## Sheet1
	26	Worked on issues during APACS to APACSVNA migration steps, including errors like inability to switch protocol from DICOM to HTTP, internal server errors, and connection failures during retries.
	27	Worked on Apacs to APACSVNA migration steps. issue: Not able to view dicom images using ui page (404 error)
	28	Worked on Apacs to APACSVNA migration steps. issue: Not able to view dicom images using ui page (404 error)
	29
	30	Successfully configured APACSVNA to retrieve DICOM images from APACS and display them on the APACSVNA UI page. I can now view all DICOM images individually.Successfully queried DICOM images(retrieved from APACS) using Falcon.
	31	Tried to view images in falcon without retrieving manually from APACS. Configured Falcon with APACSVNA to view dicom images
NOV
	1	Tried to view images in falcon without retrieving manually from APACS. But I am not able to view dicom images in Falcon without retrieving APACS images. I am working on it.
	2	Tried to view images in falcon without retrieving manually from APACS. But I am not able to view dicom images in Falcon without retrieving APACS images. I am working on it.
	3	Tried to view images in falcon without retrieving manually from APACS. But I am not able to view dicom images in Falcon without retrieving APACS images. I am working on it.
	4
	5
	6	Installed APACS license. Then APACS is installed. Attempts to send images to APACS were unsuccessful due to unexpected errors and a "connection refused" error. Additionally, some issues were encountered while starting the APACS system.
	7	Tried APACS installation using new ssclic.jar and completed it, test it by send image against it. Also tried installation using a different version of apacs installer jar file. Placed an order in his and send an dicom image against it. Had some errors in APACS Log
	8	Placed an order in his and send an dicom image against it. Tried to solve yesterday's apacs and mirth connection error
	9	Placed an order in his and send an dicom image against it. Completed all steps to hl7_mwl_configuration_apacs.docx steps regarding yesterday's issues. I am working on that issue.
	10	Placed an order in his and send an dicom image against it. Worked on previous issues. Refressed java fundamentals.
	11
	12
	13	Installed mysql 5.7.35 successfully. Working on MySQL Version Upgrade for PACS Database.
	14	Working on MySQL Version Upgrade for PACS Database. Tried to delete entries at study, series and instance level. But failed to some errors
	15	Working on MySQL Version Upgrade for PACS Database. Tried to delete entries at study, series and instance level. But failed to some errors
	16	Working on MySQL Version Upgrade for PACS Database. Tried to delete entries at study, series and instance level. Tried different mysql java connector.
	17	Worked on MySQL Version Upgrade for PACS Database. I am able to run apacs without any error when mysql-connector-java-5.1.4 is used. Tested apacs by sending and deleted images
	18	Faced issue with connecting to my old mysql server(where my most databases exists). The issue get resolved when some memory space in /DB/ is released. Tested APACSVNA. / Tested apacs by sending and deleted images.
	19
	20	Installed a new APACSVNA, Done Accessing External Archive and tried to connected it with my apacs. Tested apacsvna by sending and deleted images.
	21	Attempted to run APACS with a different MySQL connector (mysql-connector-java-5.1.25), which is used in the HIS of DMH. Faced issues like error in extracting generated keys, TransactionRolledbackLocalException in method: Java InvocationTargetException. Worked on troubleshooting and resolving these errors.
	22	Attempted to run APACS using mysql-connector-java-5.1.25, which is used in the HIS of DMH. Faced issues like error in extracting generated keys, TransactionRolledbackLocalException in method: Java InvocationTargetException. Worked on troubleshooting and resolving these errors.
	23	Attempted to run APACS using mysql-connector-java-5.1.25 and mysql-connector-java-5.1.4. Tried to resolve errors.
	24
	25
		APACS to APACSVNA Migration / Resolved migration issues like protocol switching errors (DICOM to HTTP) and 404 errors for image retrieval. / Successfully configured APACSVNA to retrieve and display DICOM images from APACS. / Integrated Falcon with APACSVNA for querying images; ongoing work to enable direct image viewing without manual retrieval. / APACS Installation & Troubleshooting / Installed APACS and resolved image transfer and connection issues. / Configured HL7 MWL and fixed Mirth connection errors. / Debugged APACS logs and refreshed Java fundamentals to address setup problems. / MySQL Upgrade & Testing / Upgraded to MySQL 5.7.35, resolving errors during database entry deletions. / Tested MySQL connectors (5.1.4, 5.1.25) for APACS compatibility; fixed database memory issues. / Validated system by transferring and deleting DICOM images. / APACSVNA Integration / Installed and configured APACSVNA with external archives. / Tested APACSVNA and resolved errors with MySQL connectors (e.g., TransactionRolledbackLocalException).